## README
PROJECT NEXUS — 3-MONTH PRODUCT ANALYST TRACKER
How to use this workbook
1. Use '3-Month Master Tracker' as the source of truth for every deliverable.
2. Update Status: Not Started → In Progress → Completed (or Blocked/Deferred).
3. Add the actual completion date and GitHub/evidence link for completed work.
4. Use 'Weekly Milestones' for the weekly view.
5. Use 'Progress Dashboard' to track completion by month.
6. Use '10 Major Artifacts' to see how the work becomes a recruiter-ready portfolio.
7. Do not build a feature unless it traces to a validated problem, requirement and success metric.
Current strategic foundation
Product DNA | Connect organizational dependencies.
Product Mission | Turn fragmented organizational information into connected, actionable business context.
Product Vision | A future where every business decision has context.
Current stage | Foundation validation / Product discovery
Role model for this project
BA | What is the business problem? Investigate processes, stakeholders, requirements and pain points.
Product / Technical Product Analyst | What should we build and why? Define product strategy, users, MVP, requirements, positioning, metrics and the business-to-technology bridge.
Development / Engineering | How do we build it? Own implementation, architecture, APIs, database, testing and deployment.

## 3-Month Master Tracker
ID | Month | Phase | Major Artifact | Deliverable | What This Should Contain | Purpose / Why It Matters | Expected Output | Priority | Status | Planned Week | Actual Completion Date | Evidence / GitHub Link | Notes
01 | Month 1 | Discover & Define | Product Strategy | Product DNA | Why the company exists | Defines fundamental purpose | Connect organizational dependencies. | Critical | Completed | Week 1
02 | Month 1 | Discover & Define | Product Strategy | Product Mission | What we do every day | Defines operating purpose | Turn fragmented organizational information into connected, actionable business context. | Critical | Completed | Week 1
03 | Month 1 | Discover & Define | Product Strategy | Product Vision | Future state if we succeed | Defines destination | A future where every business decision has context. | Critical | Completed | Week 1
04 | Month 1 | Discover & Define | Product Strategy | Product Principles | Rules guiding decisions | Prevents inconsistent choices | 3–7 product principles | High | Not Started | Week 1
05 | Month 1 | Discover & Define | Problem Discovery | Problem Statement | User, problem, impact, evidence | Creates precise problem definition | Validated enterprise problem statement | Critical | Not Started | Week 1
06 | Month 1 | Discover & Define | Problem Discovery | User Research Plan | Target users and research questions | Makes research structured | Interview/questionnaire plan | Critical | Not Started | Week 1
07 | Month 1 | Discover & Define | User Intelligence | User Personas | Goals, pains, responsibilities | Identifies users | CEO/Operations/Department/Analyst personas | Critical | Not Started | Week 2
08 | Month 1 | Discover & Define | User Intelligence | Jobs-to-be-Done | User goals/tasks | Moves beyond features | JTBD statements | High | Not Started | Week 2
09 | Month 1 | Discover & Define | User Intelligence | Pain-Point Map | Pain, frequency, severity, impact | Prioritizes problems | Pain-point matrix | High | Not Started | Week 2
10 | Month 1 | Discover & Define | Market Intelligence | Market Research | Market, trends, category | Establishes context | Market research report | High | Not Started | Week 2
11 | Month 1 | Discover & Define | Market Intelligence | Competitor Analysis | Alternatives and solutions | Avoids reinventing existing products | Competitor landscape | Critical | Not Started | Week 2
12 | Month 1 | Discover & Define | Market Intelligence | Competitive Feature Matrix | Feature-by-feature evidence | Finds gaps and positioning | Comparison matrix | Critical | Not Started | Week 3
13 | Month 1 | Discover & Define | Product Positioning | Positioning Statement | Target, category, problem, distinction | Defines market position | Positioning statement | Critical | Not Started | Week 3
14 | Month 1 | Discover & Define | Product Positioning | Differentiation Hypothesis | Potential product gap | Creates testable hypothesis | Differentiation hypothesis | Critical | Not Started | Week 3
15 | Month 1 | Discover & Define | Product Positioning | Value Proposition / Product Promise | Why users should care | Connects problem to value | Value proposition | Critical | Not Started | Week 3
16 | Month 1 | Discover & Define | Product Requirements | MVP Definition | Must/should/won't build | Controls scope | MVP scope | Critical | Not Started | Week 4
17 | Month 1 | Discover & Define | Product Requirements | Success Metrics | Measurable product outcomes | Defines success | North Star + supporting metrics | High | Not Started | Week 4
18 | Month 1 | Discover & Define | Product Requirements | PRD v1.0 | Problem, users, requirements, scope, metrics | Makes product buildable | Approved PRD | Critical | Not Started | Week 4
19 | Month 2 | Design & Engineer | Product Design | User Journey Map | Current vs future journey | Shows experience | Journey map | High | Not Started | Week 5
20 | Month 2 | Design & Engineer | Product Design | Information Architecture | Screens and navigation | Structures product | IA map | High | Not Started | Week 5
21 | Month 2 | Design & Engineer | Product Design | User Flows | Core step-by-step flows | Defines behavior | Core flows | Critical | Not Started | Week 5
22 | Month 2 | Design & Engineer | Product Design | Low-Fidelity Wireframes | Structure and interactions | Tests concepts early | Wireframes | High | Not Started | Week 6
23 | Month 2 | Design & Engineer | Product Design | High-Fidelity UI | Final screens and states | Implementation-ready design | High-fidelity screens | Critical | Not Started | Week 6
24 | Month 2 | Design & Engineer | Product Design | Design System | Components, typography, states | Maintains consistency | UI component system | Medium | Not Started | Week 6
25 | Month 2 | Design & Engineer | Technical Product Design | System Architecture | Frontend/backend/data/integrations | Defines technical solution | Architecture diagram + rationale | Critical | Not Started | Week 7
26 | Month 2 | Design & Engineer | Technical Product Design | Database Schema | Entities and relationships | Creates data foundation | ERD/schema | Critical | Not Started | Week 7
27 | Month 2 | Design & Engineer | Technical Product Design | Data Model | Events, dependencies, impacts, ownership | Defines intelligence model | Data model | Critical | Not Started | Week 7
28 | Month 2 | Design & Engineer | Technical Product Design | API Specification | Endpoints, inputs, outputs, errors | Defines contracts | API specification | High | Not Started | Week 7
29 | Month 2 | Design & Engineer | Technical Product Design | Data Pipeline Design | Ingestion, cleaning, linking, refresh | Supports trustworthy context | Pipeline design | Critical | Not Started | Week 8
30 | Month 2 | Design & Engineer | Technical Product Design | Sample Dataset | Realistic enterprise data | Enables build/demo | Synthetic/open dataset | Critical | Not Started | Week 8
31 | Month 2 | Design & Engineer | Analytics | Analytics Model | KPIs and calculations | Makes metrics reproducible | Metric definitions | High | Not Started | Week 8
32 | Month 2 | Design & Engineer | AI / Intelligence | AI/ML Architecture | Where AI adds value | Avoids unnecessary AI | AI architecture | High | Not Started | Week 8
33 | Month 2 | Design & Engineer | Technical Product Design | Technical Stack Decision | Technologies and trade-offs | Shows technical judgment | Stack decision record | High | Not Started | Week 8
34 | Month 2 | Design & Engineer | Security | Security & Access Model | Roles and permissions | Makes enterprise design credible | RBAC model | High | Not Started | Week 8
35 | Month 2 | Design & Engineer | Product Requirements | Development Backlog | Epics, stories, acceptance criteria | Translates PRD into execution | Prioritized backlog | Critical | Not Started | Week 8
36 | Month 2 | Design & Engineer | Product Management | Sprint Plan | Goals, scope, dependencies, DoD | Demonstrates delivery planning | Sprint plan | High | Not Started | Week 8
37 | Month 3 | Build, Validate & Launch | Engineering | Data Ingestion | Import and normalize events | Creates usable data | Working ingestion | Critical | Not Started | Week 9
38 | Month 3 | Build, Validate & Launch | Intelligence Engine | Dependency Engine | Link departments/events/dependencies | Core intelligence | Working dependency mapping | Critical | Not Started | Week 9
39 | Month 3 | Build, Validate & Launch | Intelligence Engine | Root-Cause Analysis | Identify contributors/causes | Answers why | Working RCA | Critical | Not Started | Week 9
40 | Month 3 | Build, Validate & Launch | Intelligence Engine | Impact Engine | Downstream business impact | Connects events to consequences | Impact calculation | Critical | Not Started | Week 10
41 | Month 3 | Build, Validate & Launch | Intelligence Engine | Ownership Engine | Responsible team/owner | Makes accountability visible | Ownership view | Critical | Not Started | Week 10
42 | Month 3 | Build, Validate & Launch | Core Experience | Decision Context View | WHY, WHO, IMPACT, dependencies, next action | Core product experience | Decision context screen | Critical | Not Started | Week 10
43 | Month 3 | Build, Validate & Launch | Intelligence Engine | Recommendation Layer | Possible next actions + rationale | Moves insight to action | Recommendation experience | High | Not Started | Week 10
44 | Month 3 | Build, Validate & Launch | Experience | Executive Dashboard | High-level context | Supports leadership decisions | Executive dashboard | Critical | Not Started | Week 11
45 | Month 3 | Build, Validate & Launch | Experience | Department View | Detailed operational context | Supports action | Department view | High | Not Started | Week 11
46 | Month 3 | Build, Validate & Launch | Experience | Dependency Graph | Visual relationships | Makes dependencies visible | Interactive graph | High | Not Started | Week 11
47 | Month 3 | Build, Validate & Launch | Experience | Event Timeline | Chronological events | Supports traceability | Timeline view | High | Not Started | Week 11
48 | Month 3 | Build, Validate & Launch | Experience | Alerts | Important changes/issues | Supports timely response | Alert mechanism | Medium | Not Started | Week 11
49 | Month 3 | Build, Validate & Launch | Governance | Decision / Audit History | Issue, decision, rationale, owner, outcome | Enables organizational learning | Decision history | High | Not Started | Week 11
50 | Month 3 | Build, Validate & Launch | Security | Authentication / RBAC | Login and access | Enterprise credibility | Working access control | High | Not Started | Week 11
51 | Month 3 | Build, Validate & Launch | Quality | Testing | Unit/integration/functional/edge tests | Ensures reliability | Test suite + results | Critical | Not Started | Week 12
52 | Month 3 | Build, Validate & Launch | Validation | User Acceptance Testing | Users perform core tasks | Validates product | UAT report | Critical | Not Started | Week 12
53 | Month 3 | Build, Validate & Launch | Validation | Usability Testing | Observe UX problems | Improves usability | Usability findings | High | Not Started | Week 12
54 | Month 3 | Build, Validate & Launch | Analytics | Product Analytics | Activation, usage, outcomes | Measures behavior | Analytics dashboard | High | Not Started | Week 12
55 | Month 3 | Build, Validate & Launch | Product Management | KPI Measurement | Results vs success metrics | Proves MVP value | MVP performance report | Critical | Not Started | Week 12
56 | Month 3 | Build, Validate & Launch | Product Management | Iteration | Evidence-based improvements | Demonstrates iteration | Updated backlog + changes | Critical | Not Started | Week 12
57 | Month 3 | Build, Validate & Launch | Release | Deployment | Deploy MVP | Makes product demonstrable | Live MVP | Critical | Not Started | Week 12
58 | Month 3 | Build, Validate & Launch | Portfolio | Product Demo | End-to-end product story | Shows value | Demo recording/script | Critical | Not Started | Week 12
59 | Month 3 | Build, Validate & Launch | Portfolio | Case Study | Problem → research → decisions → solution → results | Creates recruiter story | Written case study | Critical | Not Started | Week 12
60 | Month 3 | Build, Validate & Launch | Portfolio | Product Portfolio | Complete evidence | Shows full journey | Portfolio-ready GitHub | Critical | Not Started | Week 12
61 | Month 3 | Build, Validate & Launch | Career | Resume Project Entry | Impact-oriented bullets | Recruiter readability | Resume section | High | Not Started | Week 12
62 | Month 3 | Build, Validate & Launch | Career | Interview Case Study | 5–10 minute product story | Demonstrates thinking | Interview narrative | Critical | Not Started | Week 12
63 | Month 3 | Build, Validate & Launch | Career | Product Presentation | 10–15 slide executive deck | Demonstrates communication | Presentation deck | High | Not Started | Week 12
64 | Month 3 | Build, Validate & Launch | Retrospective | Final Retrospective | What worked, failed, changed and why | Demonstrates learning | Retrospective document | High | Not Started | Week 12

## Progress Dashboard
PROJECT NEXUS — PROGRESS DASHBOARD
Metric | Month 1 | Month 2 | Month 3 | Total
Total Deliverables
Completed
In Progress
Blocked
Completion %
Current Foundation
Product DNA | Connect organizational dependencies.
Product Mission | Turn fragmented organizational information into connected, actionable business context.
Product Vision | A future where every business decision has context.
Current stage | Foundation validation → next: UVP / Product Promise

## 10 Major Artifacts
# | Major Artifact | Purpose | Key Contents | Final Evidence
01 | Product Strategy | Define why, how and where | DNA, Mission, Vision, Principles | GitHub strategy folder
02 | Problem Discovery | Prove the problem | Problem statement, research, pain points | Research evidence
03 | User Intelligence | Understand users | Personas, JTBD, journeys | User research pack
04 | Market Intelligence | Understand alternatives | Market research, competitors, feature matrix | Competitive analysis
05 | Product Positioning | Define why us | Positioning, UVP, differentiation | Positioning document
06 | Product Requirements | Make product buildable | PRD, stories, acceptance criteria, MVP | PRD
07 | Product Design | Design experience | IA, flows, wireframes, UI | Design pack
08 | Technical Product Design | Translate into technology | Architecture, data, APIs, AI, security | Technical design
09 | Working Product | Prove it works | MVP, testing, deployment, analytics | Live demo
10 | Product Case Study | Tell the story | Decisions, trade-offs, results, learnings | Portfolio + presentation

## Weekly Milestones
Week | Month | Primary Goal | Expected Milestone | Key Deliverables | Status | Notes
1 | Month 1 | Foundation | DNA/Mission/Vision validated and documented | 01–06 | Completed
2 | Month 1 | Users + Market | Users and problem evidence mapped | 07–12 | Not Started
3 | Month 1 | Positioning | Competitive gap and value proposition defined | 13–15 | Not Started
4 | Month 1 | Scope | MVP, metrics and PRD ready | 16–18 | Not Started
5 | Month 2 | UX Architecture | Journey, IA and flows complete | 19–21 | Not Started
6 | Month 2 | UI | Wireframes and high-fidelity design complete | 22–24 | Not Started
7 | Month 2 | Technical Blueprint | Architecture, schema, data model and APIs complete | 25–28 | Not Started
8 | Month 2 | Build Readiness | Pipeline, dataset, analytics, AI, security and backlog ready | 29–36 | Not Started
9 | Month 3 | Core Engine | Ingestion, dependency and RCA foundations working | 37–39 | Not Started
10 | Month 3 | Impact + Accountability | Impact, ownership and decision context working | 40–43 | Not Started
11 | Month 3 | Experience | Dashboards, graph, timeline, alerts, history and RBAC working | 44–50 | Not Started
12 | Month 3 | Validate + Launch | Testing, UAT, metrics, deployment and portfolio complete | 51–64 | Not Started

## Role Mapping
Major Area | BA Role | Product / Technical Product Analyst Role | Development / Engineering Role | Primary Ownership
Product Strategy | Provides business context and stakeholder needs. | Owns product direction, DNA, Mission, Vision and principles. | Consults on technical feasibility. | Product / Technical Product Analyst
Problem Discovery | Owns process/problem investigation and stakeholder interviews. | Owns product problem framing and prioritization. | Provides technical constraints. | BA + Product Analyst
User Intelligence | Gathers user/stakeholder requirements. | Owns interpretation and prioritization of user problems. | Validates technical feasibility. | BA + Product Analyst
Market Intelligence | Supports research where business/process context is needed. | Owns competitive and product analysis. | Usually not involved. | Product / Technical Product Analyst
Product Positioning | Provides business/customer insight. | Owns positioning, UVP and differentiation. | Provides feasibility input when needed. | Product / Technical Product Analyst
Product Requirements | Strong contributor to business requirements. | Owns product requirements, prioritization and MVP scope. | Converts requirements into technical specifications and implementation. | Product Analyst + BA + Engineering
Product Design | Defines business workflows and process needs. | Owns user flows and product experience. | Implements technical UI/UX. | Product / Technical Product Analyst
Technical Product Design | Provides business-process input. | Acts as bridge between business and technology; translates product requirements into technical requirements. | Owns architecture, APIs, database, infrastructure and technical implementation. | Engineering + Technical Product Analyst
Working Product | Performs business/UAT validation. | Owns product acceptance, prioritization and outcome. | Builds, tests and deploys the product. | Engineering
Product Case Study | Provides business evidence and stakeholder perspective. | Owns product story, decisions, trade-offs and outcomes. | Provides technical implementation details. | Product / Technical Product Analyst

## Role Weighting
Artifact / Area | BA % | Technical Product Analyst % | Development % | What This Demonstrates
Product Strategy | 20 | 70 | 10 | Product direction and strategic thinking
Problem Discovery | 40 | 50 | 10 | Business analysis + product problem framing
User Intelligence | 40 | 50 | 10 | User/stakeholder understanding
Market Intelligence | 20 | 80 | 0 | Competitive/product thinking
Product Positioning | 10 | 90 | 0 | UVP, differentiation and positioning
Product Requirements | 30 | 50 | 20 | Requirements translation and prioritization
Product Design | 20 | 50 | 30 | Product experience + workflow thinking
Technical Product Design | 10 | 40 | 50 | Business-to-technology translation
Working Product | 5 | 25 | 70 | Product ownership + engineering execution
Product Case Study | 20 | 70 | 10 | Product decisions, trade-offs and outcomes